## Web Portal
Basils Coins Web Portal
Task | Action/Requirements | Start Date | End Date | Days | Percent | Status | Remarks
Home page | Header -Load dynamic Banners -Login/My Account/log out -Cart icon (with number of items) -Search -Logo -Dynamic Basils Coins Description -dynamic promotional message (ex. One of a kind 20% sale every day @7:00pm EST time) |  |  |  | 0% | on going
| Search Bar **search result -Category Name -Image -Name matched |  |  |  | 0% | on going
| Load Category list **Fields -Image -Category Name |  |  |  | 0% | on going
| Cart items modal **Fields -Image -Item Name -Price -Quantity -Total -View Cart Button -Check Out Button (redirect to Login page if no Session found else Check out page) |  |  |  | 0% | on going
| Load Recommended items list **Fields -Image -item Name -SRP price (cross line if has discount price) -Special Price (if has discount price) -Stock Quantity -Add to Cart Button **Condition -Top selling products |  |  |  | 0% | on going
Login / Create account page | Login **Fields -*Email -*Password Validation -Required Fields -Invalid Email or Password -Email is not yet verified please check your mail we sent for Account Verification and click Verify. -Didn't receive Account verification mail? Resend |  |  |  | 100% | Done
| Registration **Fields -*FirstName -*LastName -*Address -*City -*Country (Drop down) -*Province (Drop down) -*ZipCode -*Email -*Password -*Confirm Password -*Check box: I agree to the terms and condition (link to Terms and Condition Page) -Button: Register Validations -Email is already used, please input other email -Required fields -Confirm password does not match -Weak password -Please agree to the terms and condition | 2020-03-21 | 2020-03-21 | 1 | 80% | on going
| Email sending for Account verification -using google smtp |  |  |  | 0% | on going
| Verification Email Template -Recipient: Basils Coins -Subject: Account verification -Message: Thank you for joining us please click to verify your account -Button: Verify(link to basilscoins.com login page) |  |  |  | 0% | on going
| Activate Google smtp (for email sending) |  |  |  | 0% | on going
My Account page | Account Details (Editable) **Fields -*FirstName -*LastName -*Address -*City -*Country (Drop down) -*Province (Drop down) -*ZipCode -*Email -Save button(input current password before saving) |  |  |  | 0% | on going
| My Orders -Order list **Order reference **Order Date **Image **Name **Status -Filter (by: OrderReference ¦¦ Order Date ¦¦ Status(drop down)) / Search |  |  |  | 0% | on going
| Order Detail **Fields -Order reference -Payment Reference -Order Date -Delivery Address Sub Order Details **Items detail -Image -Name -Description -Quantity -Price **footer -Shipping fee -Sub Total -Total -paid thru [payment method] |  |  |  | 0% | on going
| Change Password **Fields -Current password -New password -Confirm new password -Button: Change password **Validation -Invalid Current password -weak new password -Confirm new password does not match |  |  |  | 0% | on going
Product Detail Page | Image -Magnify -Zoom -Selection |  |  |  | 0% | on going
| Products Details **Fields -Category Name (if Has) -Product Name -SRP (cross line if has discount ) -Special price (if has discount) -Stock quantity -Add to Cart Button / Buy now Button(redirect to Login page if no Session found else Check out page) |  |  |  | 0% | on going
| Products Description -Dynamic description display |  |  |  | 0% | on going
| Related products -Condition: With the same category |  |  |  | 0% | on going
Cart items page | Cart list **items detail -Image(thumnail) -Name -Description -Price -Quantity(changeble) -Remove icon **Footer -Sub Total -Shipping fee -Total -Check out button(redirect to Login page if no Session found else Check out page) / Shop more button |  |  |  | 0% | on going
Check out page | Customer Details **Fields -Order reference -Customer Name (First Name + Last Name) -Email Address -Delivery Address (City / Prpvince / Zip code) -Check box: use diff. Delivery Address -input diff. Delivery address |  |  |  | 0% | on going
| Cart Summary List **Columns -image -Name -Description -Quantity -Price **Footer -Sub Total -Shipping fee -Total |  |  |  | 0% | on going
| Payment Method -Payment Mehod selection with image |  |  |  | 0% | on going
| Paypal Integration for payment method -Apply Paypal Merchant -Integrate Paypal Payment Gateway API |  |  |  | 0% | on going
| Order Summary Email Template -Recipient: Basils Coins -Subject: Your Order [Order Reference] Header Basils Coins (Logo) Basils coins description Body **Message -Hi [Customer Name] -Thank you for shopping with us we recieve your order [order reference] on [Order Date] and paid thru [Payment method] with payment reference [Payment Reference]. We're getting your order ready and will let you know once it's on the way. We wish you enjoy shopping with usand hope to see you again, Thank you **Delivery Details -Customer Name -Order Date -Delivery Address -Email **Items detail -Image(thumbnail) -Name -Description -Quantity -Price **Footer -Sub Total -Shipping fee -Total -Paid thu [Payment method] |  |  |  | 0% | on going
Unique Deals page | Categories -Image -Name |  |  |  | 0% | on going
| Item List per Category **Fields -Category Name -item Image -item Name -SRP price (cross line if has discount price) -Special Price (if has discount price) -Stock Quantity -Add to Cart Button |  |  |  | 0% | on going
| Filter panel -Price : High to Low -Price : Low to High -Most popular -Availability -Search Bar |  |  |  | 0% | on going

## Web Design
Basils Coins Web Design
Task | Action/Requirements | Start Date | End Date | Days | Percent | Status | Remarks
Home page | Header -Load dynamic Banners -Login/My Account/log out -Cart icon (with number of items) -Search -Logo -Dynamic Basils Coins Description -dynamic promotional/news message (ex. One of a kind 20% sale every day @7:00pm EST time) |  |  |  | 0% | on going
| Search Bar **search result -Category Name -Image -Name matched |  |  |  | 0% | on going
| Load Category list **Fields -Image -Category Name |  |  |  | 0% | on going
| Cart items modal **Fields -Image -Item Name -Price -Quantity -Total -View Cart Button/Check Out Button |  |  |  | 0% | on going
| Recommended items list **Fields -Image -item Name -SRP price (cross line if has discount price) -Special Price (if has discount price) -Stock Quantity -Add to Cart Button |  |  |  | 0% | on going
Login / Create account page | Login **Fields -*Email -*Password |  |  |  | 0% | on going
| Registration **Fields -*FirstName -*LastName -*Address -*City -*Country (Drop down) -*Province (Drop down) -*ZipCode -*Email -*Password -*Confirm Password -*Check box: I agree to the terms and condition (link to Terms and Condition Page) -Button: Register |  |  |  | 0% | on going
| Verification Email Template -Recipient: Basils Coins -Subject: Account verification -Message: Thank you for joining us please click to verify your account -Button: Verify(link to basilscoins.com login page) |  |  |  | 0% | on going
My Account page | Account Details (Editable) **Fields -*FirstName -*LastName -*Address -*City -*Country (Drop down) -*Province (Drop down) -*ZipCode -*Email -Save button(input current password before saving - pop up) |  |  |  | 0% | on going
| My Orders -Order list **Order reference **Order Date **Image **Name **Status -Filter (by: OrderReference ¦¦ Order Date ¦¦ Status(drop down)) / Search |  |  |  | 0% | on going
| Order Detail **Fields -Order reference -Payment Reference -Order Date -Delivery Address Sub Order Details **Items detail -Image -Name -Description -Quantity -Price **footer -Shipping fee -Sub Total -Total -paid thru [payment method] |  |  |  | 0% | on going
| Change Password **Fields -Current password -New password -Confirm new password -Button: Change password **Validation -Invalid Current password -weak new password -Confirm new password does not match |  |  |  | 0% | on going
Product Detail Page | Image -Magnify -Zoom -Selection |  |  |  | 0% | on going
| Products Details **Fields -Category Name (if Has) -Product Name -SRP (cross line if has discount ) -Special price (if has discount) -Stock quantity -Add to Cart Button / Buy now Button |  |  |  | 0% | on going
| Products Description |  |  |  | 0% | on going
| Related products |  |  |  | 0% | on going
Cart items page | Cart Items **items detail -Image(thumnail) -Name -Description -Price -Quantity(changeble) -Remove icon **Footer -Sub Total -Shipping fee -Total -Check out button / Shop more button |  |  |  | 0% | on going
Check out page | Shipping Details **Fields -Order reference -Customer Name (First Name + Last Name) -Email Address -Delivery Address (City / Prpvince / Zip code) -Check box: use diff. Delivery Address -input diff. Delivery address |  |  |  | 0% | on going
| Cart Summary List **item details -image -Name -Description -Quantity -Price **Footer -Sub Total -Shipping fee -Total |  |  |  | 0% | on going
| Payment Method -Payment Mehod selection with image |  |  |  | 0% | on going
| Order Summary Email Template -Recipient: Basils Coins -Subject: Your Order [Order Reference] Header Basils Coins (Logo) Basils coins description Body **Message -Hi [Customer Name] -Thank you for shopping with us we recieve your order [order reference] on [Order Date] and paid thru [Payment method] with payment reference [Payment Reference]. We're getting your order ready and will let you know once it's on the way. We wish you enjoy shopping with us and hope to see you again, Thank you **Delivery Details -Customer Name -Order Date -Delivery Address -Email **Items detail -Image(thumbnail) -Name -Description -Quantity -Price **Footer -Sub Total -Shipping fee -Total -Paid thu [Payment method] |  |  |  | 0% | on going
Unique Deals page | Categories -Image -Name |  |  |  | 0% | on going
| Item List per Category **Fields -Category Name -item Image -item Name -SRP price (cross line if has discount price) -Special Price (if has discount price) -Stock Quantity -Add to Cart Button |  |  |  | 0% | on going
| Filter panel -Price : High to Low -Price : Low to High -Most popular -Availability -Search Bar |  |  |  | 0% | on going

## Content Management
Content Management
Task | Action | Start Date | End Date | Days | Percent | Status | Remarks
Products Maintenance | General **Fields **tProducts ID -Name -ID_Category (look up) -ID_ProductBrand (look up) -Description -SRP -Special price -StockQuantity |  |  |  | 0% | on going
| Details **Fields **tProducts_Detail -ID -ID_Products -ImageFile -ID_Color (look up) -IsPrimary |  |  |  | 0% | on going
| Image upload from tProduct_Detail (multiple upload) |  |  |  | 0% | on going
| Create/Update |  |  |  | 0% | on going
Products Category Maintenance | Fields **tCategory -ID -Name -IsActive -ImageFile -ID_Category (for parent category) |  |  |  | 0% | on going
| Create/Update |  |  |  | 0% | on going
Orders Maintenance | General **Fields **tCart ID -OrderReference -ID_Customer -IsOpen -ID_FillingStatus (look up) -ID_PaymentMethod -PaymentReference -DeliveryCharge -CustomAddress |  |  |  | 0% | on going
| Details **Fields **tCart_Detail -ID -ID_Cart -ID_Product -SubTotal -Total -Price -Quantity |  |  |  | 0% | on going
| Update |  |  |  | 0% | on going
Customer maitenance | General Fields **tCustomer ID -Name -FirstName -LastName -Address -City -ID_Country(look up) -ID_Province(look up) -ZipCode -Email -Password -DateVerified -IsActive |  |  |  | 0% | on going
| Update |  |  |  | 0% | on going